## Slide 1: Mid Semester Review Session
M K Hamirwasia
WILPD

## Slide 2
AE ZG523/DE ZG523/ES ZG523/MM ZG523/POM ZG523-Merged
Project Management
Session 11

## Slide 14
A housing project consists of activities as listed in the table. Compute the cement requirement based on early start and late start times. Also prepare a graph for cumulative cement requirement. What is the minimum and maximum requirements of cement up to the 8th week:
RESOURCE SCHEDULING, LEVELING & ALLOCATION

## Slide 15
Activity | Duration in Weeks | Total Cement Required in Tons per activity
1-2 | 4 | 20
2-3 | 4 | 24
2-4 | 6 | 18
2-5 | 2 | 10
3-6 | 2 | 20
4-6 | 8 | 24
5-6 | 4 | 20
5-7 | 6 | 30
6-7 | 8 | 40

## Slide 16
Level the resources
Allocate the resources if there is a constraint of 10 T of cement available per week and also find the duration of the project?

## Slide 17
1
2
3
4
5
6
7

## Slide 22
The expected times and variances for the project activities are given below. What is the probability of completing the project in 25 periods?
Exercise 2

## Slide 23
Exercise 2

## Slide 26
Z Values and Probabilities

## Slide 27
A-O-N
0 | 1 | 6
0 | PP | 
0 | 6 | 6
0 | 2 |  | 7
19 | SCD |  | 
19 | 7 | 26 | 
6 | 4 | 10
0 | TM | 
6 | 4 | 10
0 | 3 |  | 4
19 | DMP |  | 
19 | 4 | 23 | 
6 | 5 | 16 | 
10 | Patent |  | 
16 | 10 |  | 26
10 | 6 | 26 | 
0 | FP |  | 
10 | 16 |  | 26
4 | 7 | 7
19 | Ad Pr | 
23 | 3 | 26
CP: 1-4-6-8
TE = 28
26 | 8 | 28
0 | Release | 
26 | 2 | 28

## Slide 28
  CP: 1-4-6-8
  σTE = √ ∑ (σte )² = √3+2+10+1 = √ 16 = 4
  Z = TS – TE = 25 - 28 = - 0.75
σTE √16
P = 0.2275 (22.75 percent)
A-O-N

## Slide 29
All the Best!
M K Hamirwasia
Project Management