## Slide 1: Project Scheduling using CPM & PERT
M K Hamirwasia
WILPD

## Slide 2
AE ZG523/DE ZG523/ES ZG523/MM ZG523/POM ZG523-Merged
Project Management
Lecture No. 8

## Slide 3
  Critical Path Method (CPM) – Project Crashing
  Program/Project Evaluation and Review Technique (PERT)
PROJECT NETWORK PLANNING

## Slide 6
In 1958 the Special Office of the US Navy and the Booz, Allen, and Hamilton consulting firm developed PERT to schedule the more than 3,300 contracts of the Polaris submarine project and to cover uncertainty of activity time estimates.
PERT is almost identical to the critical path method (CPM) except it assumes each activity duration has a range that follows a statistical distribution.
PERT (PROGRAM EVALUATION & REVIEW TECHNIQUE)

## Slide 8
Activity and Project Frequency Distributions
Activity
Project
TE
a
m
b

## Slide 9
        a + 4m + b
te = -------------
6
te = weighted average activity time
a = optimistic activity time (1 chance in 100 of completing the activity earlier under normal
conditions)
b = pessimistic activity time (1 chance in 100 of completing the activity later under normal
conditions
m = most likely activity time
Weighted Average Activity Time (te)

## Slide 10
  σte = ( b – a)
  6
  σTE = √ ∑ (σte )²
Standard Deviation

## Slide 14
Ts – TE
Z = --------------
√ ∑ (σte )²
TE = Critical path duration
TS = Scheduled project duration
Z = probability (of meeting scheduled duration) found in statistical Table A7.2
Probability of Completing the Project in Time

## Slide 15
Z Values and Probabilities

## Slide 16
The activity times and variances are given in Table A7.1. The project network is presented in Figure A7.2. This figure shows the project network as AOA and AON. The AON network is presented as a reminder that PERT can use AON networks as well as AOA.
1. Compute the expected time for each activity.
2. Compute the variance for each activity.
3. Compute the expected project duration.
4. What is the probability of completing the project by day 67? Within 60 days?
A HYPOTHETICAL EXAMPLE USING THE PERT TECHNIQUE

## Slide 17
PERT Example

## Slide 20
Z Values and Probabilities

## Slide 21
PERT Example

## Slide 22
Ts – TE
Z = --------------
√ ∑ (σte )²
        67 – 64 + 3
Z = ----------------- = -------- = + 0.50
√ 25 + 9 + 1 + 1 √ 36
P = 0.69 (69 percent chance of completing the project on or before 67 time units)
Probability of completing the project in 67 days

## Slide 23
Ts – TE
Z = --------------
√ ∑ (σte )²
        60 – 64 - 4
Z = ----------------- = -------- = - 0.67
√ 25 + 9 + 1 + 1 √ 36
P = 0.26 (26 percent chance of completing the project on or before 60 time units)
Probability of completing the project in 60 days

## Slide 24
Z Values and Probabilities

## Slide 25
Given the project information below, what is the probability of completing the National Holiday Toy project in (i) 93 time units? (ii) in 88 time units?
Exercise 1
Act ID(i) | Description | Predecessor | Optm. (a) | Most likely (m) | Pess. (b) | Act. Time (te) | Variance {(b-a)/6}2 | Critical
1 | Design Package | None | 6 | 12 | 24 | 13 | 9 | Y
2 | Design product | 1 | 16 | 19 | 28 | 20 | 4 | Y
3 | Build package | 1 | 4 | 7 | 10 | 7 | 1 | N
4 | Secure patent | 2 | 21 | 30 | 39 | 30 | 9 | Y
5 | Build product | 2 | 17 | 29 | 47 | 30 | 25 | Y
6 | Paint | 3, 4,5 | 4 | 7 | 10 | 7 | 1 | N, Y, Y
7 | Test market | 6 | 13 | 16 | 19 | 16 | 1 | Y

## Slide 27
CP1: 0-1-2-4-6-7 (86)
CP2: 0-1-2-5-6-7 (86)
Exercise 1 (A-O-A)
0
1
2
4
5
3
6
7
13
20
30
7
30
7
7
7
16
TE1 = 86 Weeks
TE2 = 86
TE3 = 43

## Slide 28
A-O-N
Act ID | Description | Predecessor | Optm. (a) | Most likely (m) | Pess. (b) | Act. Time (te) | Variance {(b-a)/6}2 | Critical
A | Design Package | None | 6 | 12 | 24 | 13 | 9 | Y
B | Design product | A | 16 | 19 | 28 | 20 | 4 | Y
C | Build package | A | 4 | 7 | 10 | 7 | 1 | N
D | Secure patent | B | 21 | 30 | 39 | 30 | 9 | Y
E | Build product | B | 17 | 29 | 47 | 30 | 25 | Y
F | Paint | C, D, E | 4 | 7 | 10 | 7 | 1 | N, Y, Y
G | Test market | F | 13 | 16 | 19 | 16 | 1 | Y

## Slide 29
Z Values and Probabilities

## Slide 30
A-O-N
0 | A | 13 | 
0 | DPC |  | 
0 | 13 |  | 13
13 | C | 20
43 | BP | 
56 | 7 | 63
33 | D | 63 | 
0 | SP |  | 
33 | 30 |  | 63
13 | B | 33 | 
0 | DPR |  | 
13 | 20 |  | 33
33 | E | 63 | 
0 | BP |  | 
33 | 30 |  | 63
70 | G | 86 | 
0 | TMKT |  | 
70 | 16 |  | 86
63 | F | 70
0 | PT | 
63 | 7 | 70
CP1: A-B-D-F-G
CP2: A-B-E-F-G
TE = 86 Weeks

## Slide 31
CP1: 0-1-2-4-6-7 (TE = 86) A-O-A
CP1: A-B-D-F-G (TE = 86) A-O-N
  σTE = √ ∑ (σte )² = √9+4+9+1+1 = √ 24
  Z = TS – TE = 93 -86 = 1.428869
σTE √ 24
P = .92275 (92.28 percent)
Taking the scheduled completion time to be 88 weeks;
  Z = 88 - 86 = 2 = 0.408248, P = 0.6579
√ 24 4.899 (65.79 percent)
Exercise 1

## Slide 32
CP2: 0-1-2-5-6-7 (TE = 86) A-O-A
CP2: A-B-E-F-G (TE = 86) A-O-N
  σTE = √ ∑ (σte )² = √9+4+25+1+1 = √ 40
  Z = TS – TE = 93 -86 = 1.106797
σTE √ 40
P = .8645 (86.45 percent)
Taking the scheduled completion time to be 88 weeks;
  Z = 88 - 86 = 2 = 0.316228 P = 0.6232
√ 40 6.3245 (62.32 percent)
Exercise 1

## Slide 33
Solve Exercise 1 Using WIN QS

## Slide 34
Input the data

## Slide 35
Solve and Analyse – Solve Critical Path

## Slide 36
Results – Perform Probability Analysis

## Slide 37
The expected times and variances for the project activities are given below. What is the probability of completing the project in 25 periods?
Exercise 2

## Slide 38
Exercise 2

## Slide 39
Z Values and Probabilities

## Slide 40
A-O-N
0 | 1 | 6
0 | PP | 
0 | 6 | 6
0 | 2 |  | 7
19 | SCD |  | 
19 | 7 | 26 | 
6 | 4 | 10
0 | TM | 
6 | 4 | 10
0 | 3 |  | 4
19 | DMP |  | 
19 | 4 | 23 | 
6 | 5 | 16 | 
10 | Patent |  | 
16 | 10 |  | 26
10 | 6 | 26 | 
0 | FP |  | 
10 | 16 |  | 26
4 | 7 | 7
19 | Ad Pr | 
23 | 3 | 26
CP: 1-4-6-8
TE = 28
26 | 8 | 28
0 | Release | 
26 | 2 | 28

## Slide 41
  CP: 1-4-6-8
  σTE = √ ∑ (σte )² = √3+2+10+1 = √ 16 = 4
  Z = TS – TE = 25 - 28 = - 0.75
σTE √16
P = 0.2275 (22.75 percent)
A-O-N

## Slide 42
Thank You!
M K Hamirwasia
Project Scheduling