## Slide 1: 1. PERT Problems, Ch. 7, T1 2. Scheduling Res & Costs, Ch. 8, T1
M K Hamirwasia
WILPD

## Slide 2
AE ZG523/DE ZG523/ES ZG523/MM ZG523/POM ZG523-Merged
Project Management
Lecture No. 09

## Slide 5
Given the project information below, what is the probability of completing the National Holiday Toy project in (i) 93 time units? (ii) in 88 time units?
Exercise 1
Act ID(i) | Description | Predecessor | Optm. (a) | Most likely (m) | Pess. (b) | Act. Time (te) | Variance {(b-a)/6}2 | Critical
1 | Design Package | None | 6 | 12 | 24 | 13 | 9 | Y
2 | Design product | 1 | 16 | 19 | 28 | 20 | 4 | Y
3 | Build package | 1 | 4 | 7 | 10 | 7 | 1 | N
4 | Secure patent | 2 | 21 | 30 | 39 | 30 | 9 | Y
5 | Build product | 2 | 17 | 29 | 47 | 30 | 25 | Y
6 | Paint | 3, 4,5 | 4 | 7 | 10 | 7 | 1 | N, Y, Y
7 | Test market | 6 | 13 | 16 | 19 | 16 | 1 | Y

## Slide 8
Z Values and Probabilities

## Slide 10
CP1: 0-1-2-4-6-7 (86)
CP2: 0-1-2-5-6-7 (86)
Exercise 1 (A-O-A)
0
1
2
4
5
3
6
7
13
20
30
7
30
7
7
7
16
TE1 = 86 Weeks
TE2 = 86
TE3 = 43

## Slide 11
A-O-N
Act ID | Description | Predecessor | Optm. (a) | Most likely (m) | Pess. (b) | Act. Time (te) | Variance {(b-a)/6}2 | Critical
A | Design Package | None | 6 | 12 | 24 | 13 | 9 | Y
B | Design product | A | 16 | 19 | 28 | 20 | 4 | Y
C | Build package | A | 4 | 7 | 10 | 7 | 1 | N
D | Secure patent | B | 21 | 30 | 39 | 30 | 9 | Y
E | Build product | B | 17 | 29 | 47 | 30 | 25 | Y
F | Paint | C, D, E | 4 | 7 | 10 | 7 | 1 | N, Y, Y
G | Test market | F | 13 | 16 | 19 | 16 | 1 | Y

## Slide 12
Z Values and Probabilities

## Slide 13
A-O-N
0 | A | 13 | 
0 | DPC |  | 
0 | 13 |  | 13
13 | C | 20
43 | BP | 
56 | 7 | 63
33 | D | 63 | 
0 | SP |  | 
33 | 30 |  | 63
13 | B | 33 | 
0 | DPR |  | 
13 | 20 |  | 33
33 | E | 63 | 
0 | BP |  | 
33 | 30 |  | 63
70 | G | 86 | 
0 | TMKT |  | 
70 | 16 |  | 86
63 | F | 70
0 | PT | 
63 | 7 | 70
CP1: A-B-D-F-G
CP2: A-B-E-F-G
TE = 86 Weeks

## Slide 14
CP1: 0-1-2-4-6-7 (TE = 86) A-O-A
CP1: A-B-D-F-G (TE = 86) A-O-N
  σTE = √ ∑ (σte )² = √9+4+9+1+1 = √ 24
  Z = TS – TE = 93 -86 = 1.428869
σTE √ 24
P = .92275 (92.28 percent)
Taking the scheduled completion time to be 88 weeks;
  Z = 88 - 86 = 2 = 0.408248, P = 0.6579
√ 24 4.899 (65.79 percent)
Exercise 1

## Slide 15
CP2: 0-1-2-5-6-7 (TE = 86) A-O-A
CP2: A-B-E-F-G (TE = 86) A-O-N
  σTE = √ ∑ (σte )² = √9+4+25+1+1 = √ 40
  Z = TS – TE = 93 -86 = 1.106797
σTE √ 40
P = .8645 (86.45 percent)
Taking the scheduled completion time to be 88 weeks;
  Z = 88 - 86 = 2 = 0.316228 P = 0.6232
√ 40 6.3245 (62.32 percent)
Exercise 1

## Slide 16
Solve Exercise 1 Using WIN QS

## Slide 17
Input the data

## Slide 18
Solve and Analyse – Solve Critical Path

## Slide 19
Results – Perform Probability Analysis

## Slide 20
The expected times and variances for the project activities are given below. What is the probability of completing the project in 25 periods?
Exercise 2

## Slide 21
Exercise 2

## Slide 22
Z Values and Probabilities

## Slide 23
A-O-N
0 | 1 | 6
0 | PP | 
0 | 6 | 6
0 | 2 |  | 7
19 | SCD |  | 
19 | 7 | 26 | 
6 | 4 | 10
0 | TM | 
6 | 4 | 10
0 | 3 |  | 4
19 | DMP |  | 
19 | 4 | 23 | 
6 | 5 | 16 | 
10 | Patent |  | 
16 | 10 |  | 26
10 | 6 | 26 | 
0 | FP |  | 
10 | 16 |  | 26
4 | 7 | 7
19 | Ad Pr | 
23 | 3 | 26
CP: 1-4-6-8
TE = 28
26 | 8 | 28
0 | Release | 
26 | 2 | 28

## Slide 24
  CP: 1-4-6-8
  σTE = √ ∑ (σte )² = √3+2+10+1 = √ 16 = 4
  Z = TS – TE = 25 - 28 = - 0.75
σTE √16
P = 0.2275 (22.75 percent)
A-O-N

## Slide 25: SCHEDULING RESOURCES and COSTS, Ch. 8, T1
M K Hamirwasia
WILPD

## Slide 26
Project networks are based on two premises:
The time estimates are based on the assumption that resources will be available as required.
The sequence of activities is based on technical / logical considerations.
Scheduling Resources and Costs

## Slide 27
Resources and Priorities
  Project network times are not a schedule until resources have been assigned.
  Cost estimates are not a budget until they have been time-phased.
The Resource Problem

## Slide 29
First prepare the resource schedule (Direct costs of people, material and equipment).
Assign time-phased costs that provide the project budget baseline – PV.
Monitor progress by checking the schedule and cost variances – actual versus planned.
Scheduling Resources and Costs

## Slide 30
Project Planning Process

## Slide 31
Resource Smoothing (or Leveling)
  Involves attempting to even out varying demands on resources by using slack (delaying noncritical activities) to manage resource utilization when resources are adequate over the life of the project.
Resource-Constrained Scheduling
  The duration of a project may be increased by delaying the late start of some of its activities if resources are not adequate to meet peak demands.
The Resource Problem (cont’d)

## Slide 32
Thank You!
M K Hamirwasia
Project Management