## Slide 1: Modern Project Management (Ch. 1 – T1)
M K Hamirwasia
WILPD

## Slide 2
AE ZG523/DE ZG523/ES ZG523/MM ZG523/POM ZG523
Project Management
Second Semester 2024-25
Lecture No. 2

## Slide 3
Definition of Project Management
Evolution of Project Management
Definition of a Project
Characteristics of a Project
The Project Life Cycle
Project, Program, Portfolio
Current Drivers of Project Management
The Project Manager
Project Management Process Groups
Project Management Knowledge Areas
Project Integration Management
Some Definitions
Introduction to Project Management

## Slide 15
Basics
A project is a planned set of interrelated and sometimes dependent tasks that must be executed over a certain period of time taking into consideration certain costs, timelines, resources and other limitations. The tasks must be completed in order to reach a specific goal.
It can also be defined as a set of inputs and outputs needed to reach a specific outcome.
A project is an initiative, with a definite starting and ending point, that will result in a specific, unique outcome (product, service, solution or result). Once the desired result has been achieved, the project is complete.
Introduction to Project Management

## Slide 16
Project management covers the management of projects and their running. Not all projects are the same and vary on a number of different elements that make each project individual.
Project Management is the application of knowledge, skills, tools and techniques to project activities to meet the project objectives for launching the project.
It is through certain project management processes that we apply the knowledge, skills, tools and techniques to project activities. Project management processes are supposed to embody good management practices common to management of almost all projects.
Introduction to Project Management

## Slide 17
Intro to Project Management
Activities that go on indefinitely are typically known as processes or operations.
A project is unique; a process is repeatable and strives for consistency, standardization, and no deviation from a standard.

## Slide 18
Project Scope: This describes the reach and scale of the project. Projects can be big or small depending on the scope.
A project’s scope is the full amount of work that needs to be performed in order to achieve the desired outcome under the given conditions.
The term scope creep refers to the uncontrolled expansion of a project’s scope, which can result in major delays and excessive costs.
Plan: A plan is a strategy designed to guide and control the project so that the desired result is achieved within the desired timeframe/cost.
Introduction to Project Management

## Slide 19
Task: A task is a specific chunk of work or effort that needs to be completed in order to successfully execute the plan and achieve the desired result.
A resource is anything that is needed to complete/accomplish a project task. This includes people, equipment, materials, and other costs and expenses.
An assignment is the link between a resource and a task. In most cases, this means assigning a specific person to complete a specific chunk of work.
Introduction to Project Management

## Slide 20
Projects are comprised of one or more phases. A phase consists of a group of activities that result in the completion of one or more deliverables (eg., the foundation phase of a house includes digging the trench, assembling the forms for the basement walls, pouring the concrete, etc.). Within each phase are various project management processes, which are grouped into five process groups: 1. Initiating Process Group, 2. Planning Process Group, 3. Executing Process Group, 4. Monitoring & Controlling Process Group, and 5. Closing Process Group.
Introduction to Project Management

## Slide 21
A project charter is a document issued by the project initiator/project sponsor/top management that formally authorizes the existence of a project and provides the project manager with the authority to utilize organizational resources for the completion of the project.
Ideally, a manager just one level above the project manager in the organization hierarchy should prepare the project charter. Else, the project manager should prepare the project charter. But it is issued by the senior management/project sponsor. Please note the difference between prepare and issue!
The Project Charter vs Project Scope Statement

## Slide 22
The Project Charter (PC) and Project Scope Statement (PSS) can seem like one and the same sometimes. They are both usually contained early in the project management plan, and they both itemize the scope of the project to some extent.
Well, they have a slight difference in purpose. The PC should contain the rationale for the project, the reasons for its existence, who initiated it, and why. In other words, the core project foundation. The scope is very much a secondary function of the project charter.
The PSS tries to encompass the full scope of the project in a para or two.
The Project Charter vs Project Scope Statement

## Slide 23
The following checklist can be used for a Project Charter:
The purpose and justification of the project.
Project objectives, or other success criteria.
High level requirements (something the product or service must do or a quality it must have).
Project description.
Product characteristics.
Risks.
Basic milestones.
Sample/preliminary budget.
Stakeholders.
Critical success factors.
Roles and responsibilities of PM and/or team.
Project sponsors, clients.
The Project Charter vs Project Scope Statement

## Slide 24
The PSS can contain the following information:
Scope description.
Criteria for acceptance.
Project Deliverables.
Project Milestones.
Exclusions and constraints.
Project assumptions.
However, students may use the template given in Ch. 4 of the textbook.
The Project Charter vs Project Scope Statement

## Slide 25
Time-to-Market
Technological Complexity
Sustainable Development
Corporate Downsizing (Outsourcing)
Customer Responsiveness
Project Portfolio Management for managing many small projects
Current Drivers of PM

## Slide 26
Developed in the late 1950’s to aid planning and scheduling of large projects
Defence
Construction Industry
Aerospace
Automakers – Toyota, Nissan, BMW
Electronics
Information Technology
Steel & Cement
Fertilizer
Oil and Gas
Pharmaceutical
EVOLUTION and APPLICATION

## Slide 27
A Project is a Complex, Non-routine, One-time Effort Limited by Time, Resources and Performance Specifications Designed to Meet Customer Needs.
A Project is a Temporary Endeavour to Create a Unique Product, Service or Result.
EXAMPLES
  Introduction of a new kind of detergent in the market
  Enhancing the capacity of a plant
  Reducing the downtime of machines
  Improving the Quality of a Product
  Erection and Commissioning of a Power Plant
  Preparation of documents for takeover of a Firm
  Overhauling and Turnaround of an Oil Refinery
WHAT IS A PROJECT?

## Slide 28
CHARACTERISTICS
  A Project consists of a series of activities and tasks that
  Have a Specific Objective to be Completed within Certain Specifications
  Have Definite Start and End Dates
  Have Funding Limits
  Consume Resources (human and non-human)
  Meet and Exceed Customer Needs
  Are Multifunctional - the Involvement of Several Departments and Professionals
  Typically Involve Doing Something That has Never been Done Before.
CHARACTERISTICS, ELEMENTS AND NEEDS

## Slide 29
Project Selection
Prioritization Of Projects
Scope Of Work
Work Breakdown Structure
Risk Management
Cost and Time Estimate
Procurement
Allocation Of Resources
Execution Of Jobs
ELEMENTS OF A PROJECT

## Slide 30
Subcontracting
Regular Review
Feedback
Control
Commissioning
Final Handing Over to the Client
Evaluation of Project Manager and Team
Retrospectives
ELEMENTS OF A PROJECT

## Slide 31
Project: Fulfilling the needs and requirements of the Customer
Stakeholders: Meeting the needs of Stakeholders
Organization: Meeting the strategic needs of the organization
Individuals: Meeting the goals and aspirations of Project Manager and project team members
NEED OF A PROJECT

## Slide 32
Project Management in project-driven organizations is mature and respected. On the other hand, in non-project-driven organizations, Project Management is still in its infancy, and is often looked at with skepticism.
Project-driven organizations make the lion’s share of their income through projects; non-project-driven organizations mainly make their income through production.
The Project Manager is responsible for the profitability and loss in project-driven organizations. In non-project-driven organizations, the responsibility for profitability and loss is ambiguous.
PROJECT DRIVEN ORGANIZATION Vs NON-PROJECT DRIVEN ORGANIZATION

## Slide 33
PROJECT DRIVEN ORGANIZATION Vs NON-PROJECT DRIVEN ORGANIZATION
Project-driven organizations adopt either fully projectized or matrix organizational structures. Non-project-driven organizations usually adopt a functional organizational structure.
Project-driven organizations have flexible career paths, where one can ascend quickly to higher positions. Non-project-driven organizations have traditional career paths, where moving upwards in the company ladder is very difficult. Quite often, one has to wait for their manager to get fired/resign/retire/perish to ascend the company’s ladder and assume a better position.

## Slide 34
Examples of industries where project-driven organizations are predominant include:
Construction
Aerospace
Research
Examples of industries where non-project-driven organizations are predominant include:
Manufacturing
Services
Farming
Natural Resources
PROJECT DRIVEN ORGANIZATION Vs NON-PROJECT DRIVEN ORGANIZATION

## Slide 35
IT (Information Technology) organizations (that fall under the services industry) are considered to be hybrid, where parts of such organizations are considered to be project-driven (such as the development of a new software), while other parts are considered to be non-project-driven (for example supporting applications).
PROJECT DRIVEN ORGANIZATION Vs NON-PROJECT DRIVEN ORGANIZATION

## Slide 36
Projects may be few and far between
Not all projects have the same Project Management requirements
Executives do not have sufficient time to manage projects
Projects tend to be delayed because approvals most often follow vertical chain of command
Project staffing is on a local basis
Heavy dependence upon subcontractors and outside agencies for Project Management expertise
LIMITATIONS OF NON-PROJECT DRIVEN ORGANIZATIONS

## Slide 37
Classification of Projects
Different Sectors: Public Sector, Private Sector, Service Sector, Joint Sector
Industrial
Software
Service
Infrastructure
Construction
Expansion
Modernization
TYPES OF PROJECTS

## Slide 38
Maintenance
Plant Shutdown and Turnaround
Diversification
Integration
  Forward Integration
  Backward Integration
  Vertical Integration
Acquisition
Rehabilitation
Research and Development
Types of Projects

## Slide 39
Inadequately trained and /or inexperienced project managers
Failure to set and manage expectations
Poor leadership at any and all levels
Failure to adequately identify , document and track requirements
Poor plans and planning processes
Poor effort estimation
Cultural and ethical misalignment
WHY DO PROJECTS FAIL?

## Slide 40
Misalignment between the project team and the business or other organizations it serves
Inadequate or misused methods
Inadequate communication , including progress tracking and reporting
Why Do Projects Fail?

## Slide 41
Project Life Cycle recognizes that projects have limited span
Predictable changes in level of effort and focus over the life of the project
Stages:
  Defining Stage
  Planning Stage
  Executing Stage
  Delivery / Closing Stage
PROJECT LIFE CYCLE

## Slide 42
DEFINING
Goals
Specifications
Task
Responsibilities
PLANNING
Scheduling
Budgets
Resources
Risks
Staffing
Project Life Cycle

## Slide 43
EXECUTING
Status Reports
Changes
Quality
Forecasts
CLOSING / DELIVERY
Train Customer
Transfer Documents
Release Resources
Evaluation
Lessons Learned
Project Life Cycle

## Slide 44
Research and Development
Market Introduction
Growth
Maturity
Deterioration
Death
PRODUCT LIFE CYCLE

## Slide 45
Engineering
  Start Up
  Definition
  Main
  Termination
Manufacturing
  Formation
  Building
  Production
  Phase-out
  Final Audit
LIFE CYCLE PHASES FOR DIFFERENT PROJECTS

## Slide 46
Software Development
  Conceptual
  Planning
  Definition and Design
  Code
  Integration / Testing
  Conversion
  Maintenance
Construction
  Planning, Data Collection and Procedures
  Studies and Basic Engineering
  Major Review
  Detailed Engineering
  Construction
  Testing and Commissioning
LIFE CYCLE PHASES FOR DIFFERENT PROJECTS

## Slide 47
A project manager is a person who has the overall responsibility for the successful initiation, planning, design, execution, monitoring, controlling and closure of a project. Construction, petrochemical, architecture, information technology and many different industries that produce products and services use this job title.
The project manager must have a combination of skills including an ability to ask penetrating questions, detect unstated assumptions and resolve conflicts, as well as more general management skills.
Key among a project manager's duties is the recognition that risk directly impacts the likelihood of success and that this risk must be both formally and informally measured throughout the lifetime of a project.
The Project Manager

## Slide 48
Risks arise from uncertainty, and the successful project manager is the one who focuses on this as their primary concern. Most of the issues that impact a project result in one way or another from risk. A good project manager can lessen risk significantly, often by adhering to a policy of open communication, ensuring every significant participant has an opportunity to express opinions and concerns.
A project manager is a person who is responsible for making decisions, both large and small. The project manager should make sure they control risk and minimize uncertainty. Every decision the project manager makes must directly benefit their project.
The Project Manager

## Slide 49
Roles and Responsibilities
The role of the project manager encompasses many activities including:
Planning and Defining Scope
Activity Planning and Sequencing
Resource Planning
Developing Schedules
Time Estimating
Cost Estimating
Developing a Budget
Documentation
Creating Charts and Schedules
The Project Manager

## Slide 50
Risk Analysis
Managing Risks and Issues
Monitoring and Reporting Progress
Team Leadership
Strategic Influencing
Business Partnering
Working with Vendors
Scalability, Interoperability and Portability Analysis
Controlling Quality
Benefits Realization
Finally, senior management must give a project manager support and authority if he or she is going to be successful.
The Project Manager

## Slide 51
Team members are selected because they have particular skills that are required to complete project tasks. Examples include specialists in business or technical disciplines, or an outside supplier.
The Team Member’s role is to successfully perform the tasks that have been allocated, keeping the project manager informed of progress as well as any issues that may arise.
The role often requires team members to work on their own initiative in areas where they are the ‘experts’. This places the responsibility on them to manage their own day to day work, recognize the authority of the Project Manager and report to the Project Manager as appropriate.
Being Part of a Project Team

## Slide 52
Team membership often changes as a project moves through its development. This means there are frequently two types of team member:
Core Team Member - a full time role on the project but not necessarily for the duration of the project.
Extended Team Member - a part time role on the project . These team members will usually have their regular job to do, or they may be from an outside company.
Part of the Team Member’s role is to pay attention to the problems others may be facing. Tolerance and good communications are essential ingredients of successful project teams.
Being Part of a Project Team

## Slide 53
The responsibilities assigned to individual team members may vary but typically will include:
understanding the purpose and objectives of the project
ensuring a correct balance between project and non-project work
working to timescales and within cost constraints
reporting progress against plan
producing the deliverables/products to agreed specifications
reviewing key project deliverables/products
Being Part of a Project Team

## Slide 54
identifying issues
identifying risks associated with the project
working together as a team
contributing towards successful communication
contributing towards positive motivation
On small or specialized projects, the Team Member may also be the Project Manager.
Being Part of a Project Team

## Slide 55
Project Integration Management is a collection of processes required to ensure that the various elements of the projects are properly coordinated. It involves making trade-offs among competing objectives and alternatives to meet or exceed stakeholder needs and expectations.
In other words, Project Integration Management process comprises of activities like identifying, defining, combining, and coordinating various processes related to project.
PIM

## Slide 56
Thank You!
M K Hamirwasia
hamirwasiamk@pilani.bits-pilani.ac.in
L2 - Modern Project Management
Second Semester 2024-25 (S2-24)