## Slide 1: Developing a Project Plan Ch. 6, T1
M K Hamirwasia
WILPD

## Slide 2
AE/DE/ES/MM/POM ZG523-Merged
Project Management
Lecture No. 7

## Slide 5
The Project Network
  A flow chart that graphically depicts the sequence, interdependencies, and start and finish times of the project job plan of activities that is the critical path through the network.
    Provides the basis for scheduling labor and equipment.
    Enhances communication among project participants.
    Provides an estimate of the project’s duration.
    Provides a basis for budgeting cash flows.
    Identifies activities that are critical.
    Highlights activities that are “critical” and can not be delayed.
    Helps managers get and stay on plan.
Developing a Project Plan

## Slide 6
WBS/Work Package to Network WBS Work

## Slide 7
WBS/Work Package to Network (cont’d)

## Slide 8
Terminology
  Activity: an element of the project that requires time. It is the smallest unit of work effort consuming both time and resources.
  Merge Activity: an activity that has two or more preceding activities on which it depends.
  Parallel (Concurrent) Activities: Activities that can occur independently and, if desired, not at the same time.
  Path: a sequence of connected, dependent activities.
Constructing a Project Network

## Slide 9
  Critical path: the longest path through the activity network that allows for the completion of all project-related activities; the shortest expected time in which the entire project can be completed. Delays on the critical path will delay completion of the entire project.
  Event: the point at which one or more activities are to be completed and one or more other activities are to begin. It does not consume time or resources.
  Burst Activity: an activity that has more than one activity immediately following it (more than one dependency arrow flowing from it).
Terminology

## Slide 10
Two Approaches
  Activity-on-Node (AON)
    Uses a node to depict an activity
  Activity-on-Arrow (AOA)
    Uses an arrow to depict an activity
Constructing a Project Network (cont’d)

## Slide 13
Networks typically flow from left to right.
An activity cannot begin until all preceding connected activities are complete.
Arrows indicate precedence and flow and can cross over each other.
Each activity must have a unique identify number that is greater than any of its predecessor activities.
Looping is not allowed.
Conditional statements are not allowed.
Use common start and stop nodes.
Basic Rules to Follow in Developing Project Networks

## Slide 14
Activity-on-Node Fundamentals

## Slide 15
Activity-on-Node Fundamentals (cont’d)

## Slide 16
Network Information

## Slide 18
Koll Business Center—Partial Network

## Slide 19
Koll Business Center—Complete Network

## Slide 20
Forward Pass—Earliest Times
  How soon can the activity start? (early start—ES)
  How soon can the activity finish? (early finish—EF)
  How soon can the project finish? (expected time—ET)
Backward Pass—Latest Times
  How late can the activity start? (late start—LS)
  How late can the activity finish? (late finish—LF)
  Which activities represent the critical path?
  How long can activity be delayed? (slack or float—SL)
Network Computation Process

## Slide 21
Network Information

## Slide 23
Activity-on-Node Network

## Slide 24
Add activity times along each path in the network (ES + Duration = EF).
Carry the early finish (EF) to the next activity where it becomes its early start (ES) unless…
The next succeeding activity is a merge activity, in which case the largest EF of all preceding activities is selected.
Forward Pass Computation

## Slide 25
Activity-on-Node Network Forward Pass

## Slide 26
Subtract activity times along each path in the network (LF - Duration = LS).
Carry the late start (LS) to the next activity where it becomes its late finish (LF) unless
The next succeeding activity is a burst activity, in which case the smallest LF of all preceding activities is selected.
Backward Pass Computation

## Slide 27
Activity-on-Node Network Backward Pass

## Slide 28
Total Slack
The amount of time an activity can be delayed and not delay the project
Free Slack
The amount of time an activity can be delayed without delaying any immediately following activity
Sensitivity
  Reflects the likelihood the original critical path(s) will change once the project is initiated.
  Insensitive and Sensitive network
Determining Slack (or Float)

## Slide 29
Activity-on-Node Network with Slack

## Slide 30
Free Slack Example

## Slide 31
1. You have signed a contract to build a garage for the Simpsons. You will receive a $500 bonus for completing the project within 15 working days. The contract also contains a penalty clause in which you will lose $100 for each day the project takes longer than 15 working days.
Draw a project network given the information below. Complete the forward and backward pass, compute the activity slack, and identify the critical path.
Do you expect to receive a bonus or a penalty on this project?
Exercise

## Slide 32
ID Description Predecessor Time (days)
A Pour Foundation None 3
B Erect Frame A 4
C Roof B 4
D Windows B 1
E Doors B 1
F Electrical B 3
G Rough-in-frame C, D, E, F 2
H Door Opener E, F 1
I Paint G, H 2
J Cleanup I 1
Exercise

## Slide 34
Legend
Exercise
Early Start | Activity ID | Early Finish
Slack | Description | 
Late Start | Duration | Late Finish

## Slide 35
Exercise
0F
0 | A | 3
0 | Pr Fn | 
0 | 3 | 3
3 | B |  | 7
0 | Er Fr |  | 
3 | 4 | 7 | 
7 | D |  | 8
3 | Win |  | 
10 | 1 | 11 | 
7 | C | 11
0 | Rf | 
7 | 4 | 11
11 | G | 13 | 
0 | RiF |  | 
11 | 2 |  | 13
15 | J | 16 | 
0 | Cp |  | 
15 | 1 |  | 16
13 | I | 15
0 | Pt | 
13 | 2 | 15
10 | H | 11
2 | D O | 
12 | 1 | 13
7 | E |  | 8
3 | Drs |  | 
10 | 1 | 11 | 
7 | F | 10
1 | El | 
8 | 3 | 11
FS (H) = 2
CP: A-B-C-G-I-J
TE = 16 Days

## Slide 36
2. You are creating a customer database for the Modesto Nuts minor league baseball team. Draw a project network given the information below. Complete the forward and backward pass, compute activity slack, and identify the critical path.
How long will this project take? How sensitive is the network schedule? Calculate the free slack and total slack for all noncritical activities.
Exercise

## Slide 37
ID Description Predecessor Time (days)
A Systems Design None 2
B Subsystem A Design A 1
C Subsystem B Design A 1
D Subsystem C Design A 1
E Program A B 2
F Program B C 2
G Program C D 2
H Subsystem A Test E 1
I Subsystem B Test F 1
J Subsystem C Test G 1
K Integration H, I, J 2
L Integration Test K 1
Exercise

## Slide 38
Exercise
0 | A | 2
0 | SD | 
0 | 2 | 2
2 | C | 3
0 | SSBD | 
2 | 1 | 3
3 | F | 5
0 | PRB | 
3 | 2 | 5
5 | I | 6
0 | SSBT | 
5 | 1 | 6
6 | K | 8
0 | Intgrn | 
6 | 2 | 8
8 | L | 9
0 | InTst | 
8 | 1 | 9
5 | J | 6
0 | SSCT | 
5 | 1 | 6
3 | G | 5
0 | PRC | 
3 | 2 | 5
2 | D | 3
0 | SSCD | 
2 | 1 | 3
5 | H | 6
0 | SSAT | 
5 | 1 | 6
3 | E | 5
0 | PRA | 
3 | 2 | 5
2 | B | 3
0 | SSAD | 
2 | 1 | 3
TE = 9 Days
3 Critical Paths
Very Sensitive Network
No Free Slack

## Slide 39
Thank You!
Project Management