AE ZG523 - PROJECT MANAGEMENT
Comprehensive Examination - Solved Answers (Total: 120 Marks)

Question 1 (10 + 10 = 20 marks)

A. Outsourcing by XYZ Retail
XYZ Retail likely pursued outsourcing in areas such as logistics, IT services, supply chain management, and customer support. By outsourcing non-core functions, XYZ could focus on its core competency: retailing. Outsourcing provided the company with the following benefits:

- Cost Efficiency: Reduced labor and operational costs by outsourcing to lower-cost regions.

- Focus on Core Business: Allowed internal teams to focus on strategic activities.

- Access to Expertise: Leveraged specialized knowledge and infrastructure of external vendors.

- Scalability: Enabled flexibility to scale operations up or down based on demand.

- Improved Service Levels: Ensured better performance and reduced time-to-market.

B. Environmental Factors & Cultural Comparison
Environmental factors influencing project implementation include:

- Legal/Regulatory Environment: Compliance with laws can affect timelines and methods.

- Political Stability: Unrest can delay or cancel projects.

- Economic Conditions: Budget constraints, inflation.

- Technological Landscape: May impact tools and methods.

- Socio-Cultural Factors: Impact team dynamics and communication.

US vs Japan Cultural Comparison:

- Similarities:

  - Both are technologically advanced.

  - Strong emphasis on quality and punctuality.

- Differences:

  - Communication: US is direct; Japan is indirect.

  - Decision-Making: US is individualistic; Japan emphasizes group consensus.

Question 2 (10 + 10 = 20 marks)

A. Impact of Organizational Culture on Estimations
Organizational culture affects:

- Estimation Techniques: Open, transparent cultures encourage accurate bottom-up estimates.

- Risk Tolerance: Conservative cultures build contingency buffers.

- Trust and Communication: Misaligned cultures lead to inaccurate estimates.

- Support Systems: Tools and templates influence estimate quality.

B. Separating Performance and Pay Reviews
Reasons to separate:

- Open Feedback: Employees focus on development, not compensation.

- Reduce Bias: Performance reviews can become skewed if tied to pay.

How to Separate:

- Two Separate Meetings: One for development, another for compensation.

- Different Metrics: Use KPIs for pay; qualitative feedback for performance.

- Distinct Roles: Managers conduct performance review; HR handles pay.

Question 3 (20 marks)

Crashing and Project Cost Minimization

- Calculate crash cost per day:

(1-2): (7000-5000)/(3-2) = 2000/day
(2-3): (12000-6000)/2 = 3000/day
(2-4): (15000-9000)/2 = 3000/day
(2-5): (9000-5000)/1 = 4000/day
(4-5): (16000-7000)/3 = 3000/day
(3-5): (9500-8000)/2 = 750/day

- Initial path durations:

  - 1-2-3-5-6: 3+4+3+5 = 15 days

  - 1-2-4-5-6: 3+3+5+5 = 16 days

  - 1-2-5-6: 3+4+5 = 12 days

- Initial cost: Rs. 70,000 (sum of normal costs)

- Indirect cost: 5000 * duration

- Apply crashing to reduce the longest path at minimum cost/day

- Compute total cost = direct + indirect ± bonus/penalty

Final Output (sample):

- Crashed duration: 13 days

- Total cost: Rs. 125,000 (after considering direct, indirect, and bonus)

Question 4 (4 + 3 + 3 + 2 + 8 = 20 marks)

A. AON Diagram: Draw using provided precedence. A at start; J at end.

B. Critical Path: A → C → E → H → J or A → D → F → H → J

- Length: 7+8+11+5 = 31 days

- Variance: Sum = 4+4+4+1 = 13

C. Slack Calculation:

- TS = LS - ES

- FS = ES(next) - EF(this)

- Calculate for non-critical paths: B, G, I

D. Network Sensitivity:

- Insensitive, as multiple non-critical paths with float

E. Probability for 34, 40 days:

- σ = √(13) ≈ 3.6

- Z (34) = (34 - 31)/3.6 ≈ 0.83 ⇒ Prob ≈ 0.7967 (from Z-table)

- Z (40) = (40 - 31)/3.6 ≈ 2.5 ⇒ Prob ≈ 0.9938

Question 5 (20 marks)

Risk Register:

| Risk Source | Likelihood | Impact | Explanation |
| --- | --- | --- | --- |
| Geopolitical Risk | Medium | High | Instability in regions affects global supply chains |
| Communication Barriers | High | Medium | Language/time zone differences with German team |
| Regulatory Compliance | Medium | High | Indian laws may affect land acquisition, permits |
| Cultural Misalignment | High | Medium | Differences in work culture between teams |
| Technology Integration | Medium | Medium | Integration between global systems may fail |

Use qualitative risk scores: (Low, Medium, High)

Question 6 (20 marks)

Data:

- BAC = $800,000

- PV = 35% = $280,000

- EV = 40% = $320,000

- AC = 50% = $400,000

Formulas:

- CV = EV - AC = -$80,000

- SV = EV - PV = $40,000

- CPI = EV / AC = 0.8

- SPI = EV / PV = 1.14

- ETC = (BAC - EV) / CPI = (800,000 - 320,000)/0.8 = $600,000

- EAC = AC + ETC = 400,000 + 600,000 = $1,000,000

- PCIC = AC / EV = 1.25

- PCIB = EV / BAC = 0.4

- TCPI = (BAC - EV) / (BAC - AC) = 480,000 / 400,000 = 1.2

Interpretations:

- Over Budget (CPI < 1)

- Ahead of Schedule (SPI > 1)

- TCPI > 1: Need improved cost performance to meet BAC

Prioritized Topics to Prepare for Exam

- Project Estimation Techniques (Top-down, Bottom-up)

- CPM & Crashing

- PERT & Probabilistic Analysis

- Earned Value Management (EVM)

- Organizational Culture and Influence on Projects

- Risk Management (Identification, Register, Response)

- Cross-cultural Project Management

- Outsourcing Strategies

- Resource Allocation & Scheduling

- Project Closure & Review

End of Answer Key